## 1B. Use case based est.
Project and task planning
Customer: | Bibliosoft
Project: | Time Off Tracker
Date: | 2024-04-12
Author: | Syed Amanullah
Use case time multiple: | 40 | (This is a time multiple used to estimate the project, set it to a number you think is appropriate - it depends on the average size of your use cases)
Instructions
A Use-case is a functional/logical aspect of the solution. That means that is not technical - it is rather the perspective of the user. E.g. "Print invoice", "Print Collective Invoice" or "Change marketing message for correspondence letters", "Send e-invoice", "View bills to customer when recieveing call center call" etc etc. Every use case describes a process with value to the end user. The use case does not describe technical things like "installation StreamServe". To use this planning template you must possess very good skills in understanding the needs of a customer and to express the functionality of a solution with the customers words. You must also have good PM skills since you will need to take into account planning, specifications, meetings, mgmt overhead, installation, configuration etc etc on every row of the time estimation WITHOUT spellingt it out (everything is included in this estimation).
1=LOW, 2=MEDIUM, 3=HIGH (you may use more levels if needed)
Use case name/number | Level of complexity | Comment
Calendar contorl individual Employees view with summary of time off requests,edit and delete | 1
Calendar contorl manager view with summary of time off requests awaiting for approval / reject | 2
Employee View status of time off requests | 1
Approve / Deny Time off Request for manager | 2
Assign Employees to managers for Admin | 3
Time off request workflow should go to managers for approval
Time off calculations while submitting request
Dataverse Data modeling after getting required information from client
Role based access planning and implementation
Functional testing in both dev and qa environment
solution deployment planning between environments using Azure Devops
Integration with Power BI for generating insightful reports on time-off trends, usage, and team analytics.
Adequate training and support to ensure smooth adoption by employees and managers.
Risks and external system or data integration or migration
Sum: | 360 | (this is the time for the whole project)